## AGILE ROADMAP
QUARTER | MILESTONES | EXPECTED OUTCOME
Q1: Research & Planning | Conduct market research on accessibility needs and competitors. | Clear product scope and user requirements.
| Define core features (sign-to-text, text-to-sign, voice-to-text, and real-time translation). | Functional requirements document and user personas.
| Establish partnerships with video conferencing platforms for API integration. | Initial agreements with potential partners.
| Develop an initial product backlog and sprint planning. | Development team and tools set up.
Q2: Prototype & MVP Development | Develop a working prototype with basic sign-to-text translation. | Functional MVP with basic sign language recognition.
| Implement real-time text-to-sign conversion using avatars. | Usability feedback from early testers.
| Implement speech-to-sign translation using an animated avatar. | Initial integration success with one video conferencing platform.
| Design and develop the animated avatar for sign language translation. | Initial animated avatar prototype ready for testing.
| Integrate with at least one major video conferencing platform. | Basic UI prototype ready for testing.
| Begin internal testing and collect feedback from hearing-impaired users. | Backend infrastructure in place.
Start front-end UI design and development.
Set up backend architecture for real-time translation processing.
Q3: Beta Testing & Enhancements | Expand translation accuracy and optimize latency. | Improved AI model with enhanced accuracy.
| Integrate with multiple video conferencing platforms (Zoom, MS Teams, Google Meet). | Broader platform compatibility.
| Implement voice-to-text functionality for real-time captions. | Beta testers validating the effectiveness and usability of BRIDGE.
| Improve speech-to-sign translation accuracy and avatar fluidity. | More intuitive UI with enhanced accessibility.
| Enhance the animated avatar’s gestures and expressions for better communication. | More natural and accurate avatar sign language interpretation.
| Conduct beta testing with a wider audience, including sign language interpreters. | Optimized backend for increased user load.
Refine UI/UX based on user feedback.
Enhance backend performance for scalability.
Q4: Launch & Continuous Improvement | Release the full version of BRIDGE to the public. | Official product launch with marketing strategies.
| Establish a customer support and feedback system. | Ongoing bug fixes and performance enhancements.
| Market the product to businesses, educational institutions, and government agencies. | User adoption and positive reception in the accessibility community.
| Plan future iterations based on user feedback. | Stable, scalable backend infrastructure.
Continue refining UI and backend for improved performance.

## PROJECT SETUP AND SCOPE
PROJECT TITLE: | BRIDGE
DESCRIPTION
SCOPE
LIMITATION

## PROJECT PLANNING
QUARTER | MILESTONES | EXPECTED OUTCOME
Q1: Research & Planning | Conduct market research on accessibility needs and competitors. | Clear product scope and user requirements. | TEAMS | DEVELOPER | TESTER | SYSTEM ANALYST | MARKET ANALYST
| Define core features (sign-to-text, text-to-sign, voice-to-text, and real-time translation). | Functional requirements document and user personas.
| Establish partnerships with video conferencing platforms for API integration. | Initial agreements with potential partners. | SPRINTS
| Develop an initial product backlog and sprint planning. | Development team and tools set up.
Q2: Prototype & MVP Development | Develop a working prototype with basic sign-to-text translation. | Functional MVP with basic sign language recognition.
| Implement real-time text-to-sign conversion using avatars. | Usability feedback from early testers.
| Implement speech-to-sign translation using an animated avatar. | Initial integration success with one video conferencing platform.
| Design and develop the animated avatar for sign language translation. | Initial animated avatar prototype ready for testing.
| Integrate with at least one major video conferencing platform. | Basic UI prototype ready for testing.
| Begin internal testing and collect feedback from hearing-impaired users. | Backend infrastructure in place.
Start front-end UI design and development.
Set up backend architecture for real-time translation processing.
Q3: Beta Testing & Enhancements | Expand translation accuracy and optimize latency. | Improved AI model with enhanced accuracy.
| Integrate with multiple video conferencing platforms (Zoom, MS Teams, Google Meet). | Broader platform compatibility.
| Implement voice-to-text functionality for real-time captions. | Beta testers validating the effectiveness and usability of BRIDGE.
| Improve speech-to-sign translation accuracy and avatar fluidity. | More intuitive UI with enhanced accessibility.
| Enhance the animated avatar’s gestures and expressions for better communication. | More natural and accurate avatar sign language interpretation.
| Conduct beta testing with a wider audience, including sign language interpreters. | Optimized backend for increased user load.
Refine UI/UX based on user feedback.
Enhance backend performance for scalability.
Q4: Launch & Continuous Improvement | Release the full version of BRIDGE to the public. | Official product launch with marketing strategies.
| Establish a customer support and feedback system. | Ongoing bug fixes and performance enhancements.
| Market the product to businesses, educational institutions, and government agencies. | User adoption and positive reception in the accessibility community.
| Plan future iterations based on user feedback. | Stable, scalable backend infrastructure.
Continue refining UI and backend for improved performance.

## AGILE TEAM AND ROLES
ROLES AND RESPONSIBILITIES |  |  | TEAMS | DEVELOPER | TESTER | SYSTEM ANALYST | MARKET ANALYST
NAME | ROLES | RESPONSIBILITY

## USER STORIES AND REQUIREMENTS
functional requirements
non functional requirements
development toold
testing tools